## CIL
CONFIGURATION ITEM LIST OF FOODIES WEB APP
CI UNIQUE IDENTIFIER | CI FILE NAME | LOCATION (FOLDER) | CI DESCRIPTION | CI CONFIGURATION LEVEL | VERSION | DOCUMENTATION LINK | READ | WRITE
CI_001 | ConfigurationItemList.xlsx | Foodies/2-Reqs/ | The file where the work products files information in | version control | V 1.0 | https://github.com/sohip-a/Foodies/blob/main/2-Reqs/ConfigurationItemList.xlsx | The whole team | The whole team
CI_002 | CRS.xlsx | Foodies/2-Reqs/ | The file where the customer requirements are written and given IDs | version control | V 1.0 | https://github.com/sohip-a/Foodies/blob/main/2-Reqs/CRS.xlsx | The whole team | The whole team
CI_003 | SIQ18-02-2023.xlsx | Foodies/2-Reqs/SIQ | The file where the questions regarding CRS are written to be sent to the customer | version control | V 1.0 | https://github.com/sohip-a/Foodies/blob/main/2-Reqs/SIQ/SIQ18-02-2023.xlsx | The whole team | The whole team
CI_004 | SRS.docx | Foodies/1-PM/ | The file where the software requirements are written in user stories format | version control | V 1.0 | https://github.com/sohip-a/Foodies/blob/main/1-%20PM/SRS.docx | The whole team | The whole team
CI_005 | PMP.docx | Foodies/1-PM/ | The file where the project plan is written | version control | V 1.0 | https://github.com/sohip-a/Foodies/blob/main/1-%20PM/PMP.docx | The whole team | The whole team
CI_006 | MOM-21-02-2023.docx | Foodies/6- MinutesOfMeeting/ | MOM of 21-02-2023 | Archive | - | https://github.com/sohip-a/Foodies/blob/main/6-%20MinutesOfMeeting/MOM-22-02-2023.docx | The whole team | The whole team
CI_007 | MOM-22-02-2023.docx | Foodies/6- MinutesOfMeeting/ | MOM of 22-02-2023 | Archive | - | https://github.com/sohip-a/Foodies/blob/main/6-%20MinutesOfMeeting/MOM-22-02-2023.docx | The whole team | The whole team
CI_008 | Risk Management Policy.doc | Foodies/1-PM/ | The file where the Risk Management Policy is written | version control | V 1.0 | https://github.com/sohip-a/Foodies/blob/main/1-%20PM/Risk%20Management%20Policy.doc | The whole team | The whole team
CI_009 | Food Web App - Risk management log.xlsx | Foodies/2-Reqs/ | The file where the Risk Management Policy is written | version control | V 1.0 | https://github.com/sohip-a/Foodies/blob/main/2-Reqs/Risk%20management%20log.xlsx | The whole team | The whole team
CI_010 | RTM.xlsx | Foodies/1-PM/ | The file where the Requierment Traceability matrix is written | version control | V 1.0 | https://github.com/sohip-a/Foodies/blob/main/1-%20PM/RTM.xlsx | The whole team | The whole team
CI_011 | SIQ22-02-2023.xlsx | Foodies/2-Reqs/SIQ | The file where the questions regarding CRS are written to be sent to the customer | version control | V 1.0 | https://github.com/sohip-a/Foodies/blob/main/2-Reqs/SIQ/SIQ22-02-2023.xlsx | The whole team | The whole team