## Food Web App - Risk management
Food Web App - Risk management log
ID | Current Status | Risk Impact | Likelhood of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Risk Response Strategy | Response Strategy
RI_1 | Open | Medium | Medium | Yellow | Current developers number is limited if any developer has an emergency situation or can't continue the project for any reason the project timeline will be affected. | If any one from developers team left project schedule may slip and possibly restrict the accomplishment of project goals. | Project Resources Budget Schedule | Mitigation | Find internal resource that meets required skill and be available through project timeline or increasing work load on current team members.
RI_2 | Open | High | High | Red | current developers experinces is limited in development specially in Backend section | the project schdule will be delayed and extra budget will be required | Budget Schedule | Mitigation | provide the developers suitable training and enough time to practice their tasks
RI_3 | Open | Low | Low | Green | License for tools or OS may be expired and have to be renewed. | If the tools license is expired some teams can't continue their job and the project schedule may slip and possibly restrict the accomplishment of project goals. | Budget Schedule | Avoidance | The IT support team will renew the licenses.
RI_4 | Open | High | Medium | Red | The wrong estimation of the project schedule the project timeline is not enough to end the project. | If there was a deviation of project schedule the project won't release with all the agreed features. | Schedule | Mitigation | The current team will work overtime to close all features.
RI_5 | Open | High | Medium | Red | Unavailability of stockholder | if the client/stakeholder is not avaliable this will cause some blocks in the development | Project Resources Budget Schedule | Mitigation | Determine which stakeholder will have an influence on the current part you are working on it Always Try to have a weekly meeting with them as to communicate with them the progress takes their feedback in early stages
RI_6 | Open | Medium | High | Red | In the middle of the project, client will say that he won't continue | the project will stop | Project Resources Budget Schedule | Avoidance | the customer found a cheaper company
RI_7 | Open | High | Medium | Red | loss of remote work product | the project schdule will be delayed | Project Resources Budget Schedule | Mitigation | we have created a backup copy linked on jira tool and uploaded on google drive
RI_8 | Open | Medium | High | Red | customer required a change during sprint | the project schdule will be delayed | Project Resources Budget Schedule | Accept | change strategy is discussed in the SRS
Notes or comments:
Version # | Issued | Date | Approved | Approval
| By |  | By | Date
1 | Nader Abdallah | 22-2-2023