## Sheet1
ID | DECRIPTION | ISUUED BY | current state | refliction on this state | risk | action | Impact level
Change_Request4 | Postpone menu item page , confirmation page SRS-US-06 , SRS-US-07 | sohip ahmed | did not developed till now | will not be shown at our APP at this current release | Mentioned pages will take time and effort at coding so it will delay our team from delivering the rest of important features | need your approve for this change to be referred at next release | high