## Sheet1
ID | DECRIPTION | ISUUED BY | current state | refliction on this state | risk | action | Impact level
Change_Request1 | change in the team members"removing nader and replacing him with Aml mostafa" | omar bakr | nader is responsible form many task front end at software so he was understand the system well , | reassign this task to the new member | training new member for new technology to hand over the current tasks | spending extra time for training aml the new member to know the system well , it will be around one week | high
Change_Request2 | change in the requirments "Remove loyalty points feature" | omar bakr | loyality point features is implemented alreadly at the code , SRS (SRS-US-10), RTM , Design(AD-008), ERD | loyality point feature will be removed from the Code , SRS (SRS-US-10), RTM , Design(AD-008), ERD | the refinment of all work products will take time |  | medium
Change_Request3 | Postpone upload logo feature at SRS-A-01 (Add Restaurant page) and item logo at SRS-A-02 (Add Menu Item page) | sohip ahmed | logo feature at SRS-A-01 (Add Restaurant page) and item logo at SRS-A-02 (Add Menu Item page) did not developed till now | logo feature at SRS-A-01 (Add Restaurant page) and item logo at SRS-A-02 (Add Menu Item page) will not be shown at our APP at this current release | the restaurant logo and menu item logo will take time and effort at coding so it will delay our team from delivering the rest of important features | need your approve for this change to be referred at next release | medium