## weekly progress (hidden)
week | delivery | status
Week 1 | SRS
| SIQ | done
| PMP | done
| CIL | done
| CM Tool | done
| Schedule | done
Week 2
Week 3 | SRS
| SIQ | done
PMP
CIL
CM Tool
Schedule
Week 4
Week 5

## RACI
Task | sohib | nader | menna | abdallah | mahmoud
Release 1
SRS | I | R | S | R | S | Responsible | R
SiQ | I | A | S | R | S | Support | S
Schedule | S | I | R | I | R | review | V
PMP | R | V | R | V | R | Informed | I
CM Tool | V | R | I | I | V
Release 2
ERD | I | V | R | V | S
Activity diagram | V | I | I | R | V
Class diagram | S | S | V | I | R
UI Design | V | R | S | S | I
Release 3

## SRS (hidden)
use case name | Login
use case ID | uc-01
CRS number | 1
type | functional
Discription | user will have to create thier account using email & strong password
pre-conditions
actor
steps
Expectation

## traceability matrix (hidden)
Traceability Matrix
CRS Information |  |  | SRS Information |  | Design Information |  | Code Information |  | Test case Information |  | bug report Information
CRS.ID | Discription | PRIORITY | SRS.ID | Discription | Design.ID | Discription | Feature.ID | Discription | TC.ID | Discription | bug.ID | Discription | status
CRS-01 | Users will have to create their account using email and a strong password. | High | SRS-US-01 | Create account using email and a strong password |  |  | FT-01 |  | TC-01
|  |  | SRS-US-02 | Login to the website using my email or id and password
|  |  | SRS-US-03 | Change my password
CRS-02 | Users will be redirected to home screen activity with allnearby restaurants listed and a search box to search andselect them and to set an order. | High | SRS-US-04 | Find all nearby restaurants
|  |  | SRS-US-05 | Be able to use search box in home page
CRS-03 | Offers and promotion screen shall list all the promos andoffers from the nearby restaurants | Medium | SRS-US-06 | Find a promotion and offer in home page
CRS-04 | A credit based system from which the more the users usesthe app the more loyalty points he gets so he get more offers | Low | SRS-US-07 | Have loyalty points